## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Google | Sekilas tentang Google | Suriyadi | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Pendiri Google | Adjie Guswanda | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Produk Google | Prayogo | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Produk - Aplikasi Pencarian | Adjie Guswansa | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Produk - Telepon Genggam | Prayogo | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Sejarah Google | Fachri | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Produk - Komunikasi | Suriyadi | 5 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Prinsip Google | Fachri | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Produk - Hiburan | Prayogo | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Tampilan Produk - Produk Google | Suriyadi | 5 | 5 | 5 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Google | Kebiasaan dan Budaya Google | Adjie Guswanda | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google | Produk - Periklanan | Fachri | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0
Google | Google Games | Adjie Guswanda | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
Google | Produk - Google Lainnya | Prayogo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 1 | 0 | 0 | 0
Google | Google Activity | Suriyadi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0
Google | Hal yang google yakini | Adjie Guswanda | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0
Google | Prestasi Google | Prayogo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
Google | Edit Tampilan Presentasi | Suriyadi | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0
Google | Tim Pengelola Google | Fachri | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 0
Ideal - Remaining efforts in uninterrupted working hours |  |  | 69 | 63.25 | 57.5 | 51.75 | 46 | 40.25 | 34.5 | 28.75 | 23 | 17.25 | 11.5 | 5.75 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 69 | 63 | 54 | 47 | 37 | 32 | 28 | 23 | 20 | 15 | 9 | 3 | 0
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on H5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on I5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered